## MAS Gantt Chart
Gantt Chart
Member Application Solution |  |  | DURATION (days)
START DATE | END DATE | DESCRIPTION
2018-02-01 | 2018-02-18 | Business Process Analysis | 17
2018-02-16 | 2018-02-28 | Requirements elicitation | 12
2018-02-20 | 2018-03-01 | Document Requirements | 11
2018-02-24 | 2018-03-14 | Develop Design | 20
2018-03-10 | 2018-03-24 | Develop GIN Application | 14
2018-03-17 | 2018-03-30 | Develop LN Application | 13
2018-03-20 | 2018-04-04 | Develop Data Access Application | 14
2018-04-01 | 2018-04-14 | Testing (Integration/UAT) | 13
2018-04-15 | 2018-04-17 | Deployment | 2