## WBS + Estimates
Work Breakdown Structure | [6 empty] | Booking Management System
| Project Start | 31/12/2017
Level | WBS | Task Description | Assigned To | Start date | End date | Estimation, md | Notes
1 | 1 | Requirements Phase |  |  |  | 129
2 | 1.1 | Business Process Analysis |  |  |  | 52
3 | 1.1.1 | Define current business process |  |  |  | 12
3 | 1.1.2 | Define "to be" business process |  |  |  | 20
3 | 1.1.3 | Define state transition diagrams |  |  |  | 20
2 | 1.2 | Requirements elicitation and definition |  |  |  | 48
3 | 1.2.1 | Define and write Use Cases |  |  |  | 36
3 | 1.2.2 | Verify Use Cases |  |  |  | 7
3 | 1.2.3 | Develop Logical Data Model |  |  |  | 5
2 | 1.3 | Document Requirements |  |  |  | 29
3 | 1.3.1 | Write Requirements Document |  |  |  | 14
3 | 1.3.2 | Verify Requirements Document |  |  |  | 4
3 | 1.3.3 | Refine Impact Analysis |  |  |  | 4
3 | 1.3.4 | Refine Risk Analysis |  |  |  | 3
3 | 1.3.5 | Sign-off requirements |  |  |  | 4
1 | 2 | Design Phase |  |  |  | 62
2 | 2.1 | Design Prototyping |  |  |  | 16
2 | 2.2 | Develop Detailed Design |  |  |  | 38
2 | 2.3 | Verify Detailed Design |  |  |  | 8
1 | 3 | Development Phase |  |  |  | 94
2 | 3.1 | Develop System Components |  |  |  | 85
3 | 3.1.1 | Develop Physical Storage (Persistent Layer) |  |  |  | 22
3 | 3.1.2 | Develop BMS integration services (Backend) |  |  |  | 41
3 | 3.1.3 | Develop UI (Frontend) |  |  |  | 22
2 | 3.2 | Unit Tests |  |  |  | 9
1 | 4 | Testing Phase |  |  |  | 86
2 | 4.1 | Integration Testing |  |  |  | 18
2 | 4.2 | UAT |  |  |  | 48
2 | 4.3 | Write Help Desk Instructions |  |  |  | 10
2 | 4.4 | Conduct communication activities |  |  |  | 10
1 | 5 | Deployment Phase |  |  |  | 34
2 | 5.1 | DevOps Activities (prepare env, rollout) |  |  |  | 12
2 | 5.2 | System support |  |  |  | 22
|  | TOTAL |  |  |  | 405

## Resource Plan
Resource Plan
Resource Plan | Total days | Project time line |  |  |  | Hourly rate | Cost
Months
|  | 1 | 2 | 3 | 4
Project Team
Tech Lead | 73.5 | 1 | 1 | 1 | 0.5 | £ - | £ -
Senior Developer | 73.5 | 1 | 1 | 1 | 0.5 | £ - | £ -
Developer | 73.5 | 1 | 1 | 1 | 0.5 | £ - | £ -
| 0 |  |  |  |  | £ - | £ -
£ -
TOTAL | 220.5 | [5 empty] | £ -
[6 empty] | Contingency | 0%
£ -